## Slide 1
AUTODESK
For your reaction, not your adoption
Emi's Operating System
A light, flexible operating model that flexes between diagnosing a problem
and building something new — and the system that runs the overhead.

## Slide 2
An operating system for the role
Diagnose or build. Make it work. Hand it back.
AUTODESK
2 / 17

## Slide 3
AUTODESK
3 / 17
FRAMING
This role is ambiguous by design
I drop into very different initiatives, and the teams I direct change every time.
So this isn't a process to impose — it's a light operating system that flexes between diagnosing a problem and building something new.
Here's how I'm thinking about running my piece.
Tell me where this breaks.

## Slide 4
AUTODESK
4 / 17
THE AUTHORITY BOUNDARY
What I own — and what I don't
I own
The framing
The sequencing
The visibility
The clean handover
Their manager owns
Their roadmap
Their people's time
The capacity trade-off when priorities shift
Which is exactly why the buy-in cascade exists: I secure the manager who owns the time, not just the person.

## Slide 5
AUTODESK
5 / 17
THE SPINE
Six phases, two modes
A light lifecycle, not a heavy PMO — diagnose-mode and build-mode flex per initiative.
01
Intake
Gate, not inbox
02
Plan
Capacity cascade
03
Mobilise
Minimum spine
04
Execute
Exception only
05
Closeout
Signed handover
06
Portfolio
Generated view
DIAGNOSE MODE
Ends in a recommendation and a decision-maker
BUILD MODE
Ends in a working thing and an owner

## Slide 6
AUTODESK
6 / 17
PHASE 1
Intake is a gate, not an inbox
One front door, so work stops arriving ad hoc. The power isn't tidiness — it's the evidenced no.
Triage at the door: take / defer / decline / redirect — with a one-line logged rationale tied to current capacity.
Handover bar and receiving owner co-authored here, at the start — not at the end.
INTAKE FORM
Sponsor & decision-maker
Problem in one sentence
Desired outcome and how we'll know
People available and their managers
Who loses something if this succeeds?
Handover owner (named now)
DIAGNOSE
BUILD
TRIAGE DECISION
TAKE
DEFER
DECLINE
REDIRECT

## Slide 7
AUTODESK
7 / 17
PHASE 2
Plan: capacity is borrowed, not owned
The buy-in cascade: leadership names partners → org-level buy-in → managers release the time.
A written, lightweight commitment per contributor — person, manager, [hrs/week], duration.
RAPID for the few decisions that matter; name the Decider. RACI only for delivery tasks.
01 — Leadership
Names the established partners
02 — Org level
Buy-in confirmed across divisions
03 — Management
Secures the manager who owns the time
RAPID — decision rights
R
A
P
I
D
Decider named explicitly

## Slide 8
AUTODESK
8 / 17
PHASE 3
Mobilise: a minimum shared spine
A recommended five-folder default; the team can reshape it, as long as the decisions log and the handover folder survive.
Truly non-negotiable is tiny: one channel, one place decisions are logged, one definition of done.
Everything else the team shapes. The standard's only job is to make autonomy safe and kill status meetings.
01_Charter
Intake brief, sponsor, success metric
02_Plan
Sequence, milestones, roles
03_Working
The actual artefacts
04_Decisions & Actions
The log the status-scrape reads
Non-negotiable
05_Handover
Built continuously — closeout is assembly
Non-negotiable
"I ask three things of a project so I never have to ask you for an update."

## Slide 9
AUTODESK
9 / 17
PHASE 4
Execute by exception — no status meetings
The trade: keep three things current — decisions, open actions, blockers/risks — and I'll never book a status meeting.
The system surfaces exceptions, not status: slipped milestones, red RAID items, blocked dependencies, silence.
Silence is a signal. The most dangerous status is the absence of one.
LIVE EXCEPTION FEED
Taito onboarding
Updated 2 hrs ago · 3 actions open
ON TRACK
Inner-source model
Updated 4 hrs ago · milestone due Fri
ON TRACK
Contribution process
Milestone slipped 3 days · dependency open
AT RISK
Security sign-off
Blocked 5 days — auto-escalates to management
BLOCKED
Handover documentation
No update in 6 days
GONE QUIET

## Slide 10
AUTODESK
10 / 17
PHASE 5
Handover: a signed bar and an end date
Verify against criteria agreed up front — don't invent the bar under time pressure at the end.
Owner signs: accepted owner, SOP run once unaided, metric instrumented, escalation named, support window with an explicit end date.
For inner-source, the bar must also answer: who are the maintainers, what's the contribution and merge process, who owns triage — questions for you, not assumptions.
HANDOVER CHECKLIST
Named accountable owner has accepted
SOP exists and owner has run it once unaided
Success metric is instrumented and being watched
Escalation path and on-call are named
Support window defined — after [date], it is fully theirs
END DATE
Benefits-realisation check-back at [30/60/90] days — so "did it work" has an answer beyond "we handed it over cleanly"

## Slide 11
AUTODESK
11 / 17
PHASE 6
Portfolio: generated, never maintained
One row per initiative; three flags only — health (RAG), a people heat-map, cross-initiative dependencies.
The heat-map flags anyone load-bearing on 3+ initiatives — the silent-bottleneck detector.
Learnings library is a by-product of every closeout, so Manufacturing can reuse AEC's playbook instead of relearning it.
PORTFOLIO REGISTER
Initiative
Mode
Phase
RAG
Handover
Taito onboarding
Build
Execute
Q3
Inner-source model
Diagnose
Plan
Q4
Contribution process
Build
Mobilise
Q4
PEOPLE HEAT-MAP
Taito
Inner-src
Contrib
Person A
●
●
○
Person B
●●●
●●●
●●●
Person C
○
●
●
Person B: load-bearing on 3 initiatives — silent bottleneck

## Slide 12
What I'd build over time
The system runs the overhead.
AUTODESK
12 / 17

## Slide 13
AUTODESK
13 / 17
THE ENGINE
One engine, three faces
(what I'd build over time)
Ingest → Normalise to one schema → AI maps to a template → Standard output → the doc plus a 90-second clip.
Same engine powers Phase 4 status, Phase 5 handover and Phase 6 portfolio — just a wider window each time.
Conceptual future state, subject to your security review. Day one is a manual drop-zone: paste a transcript, get a brief.
Ingest
Drop-zone today · connectors later
→
Normalise
One schema, 7 record types
→
AI processing
Extractive, not generative
→
Standard outputs
Status · Handover · Portfolio
→
HUMAN APPROVES
→ Delivery: doc + 90-sec clip + assistant
cite-back to source on every generated line

## Slide 14
AUTODESK
14 / 17
GOVERNANCE
Built to pass a security review, not to need an exception
Governed model
Runs inside Autodesk's approved stack — zero retention, no training on our data, no consumer accounts.
Inherited permissions
Derived artefacts inherit source permissions — if you can't see the team-site, you can't see its status.
Human in the loop
A human approves every leadership-facing output. Every line cites its source. The model is never the final author.
Manual
Heavy editing
Assisted
Spot-check
Exception-only
Review flags
The trust dial turns as accuracy is proven — starts at Manual, moves right.

## Slide 15
AUTODESK
15 / 17
THE GAP
There's no PM seat — this is how we cover it
The intake form, the scaffold, the doc-scrape status and the templated handover are the PM function, systematised.
I'm not asking for headcount on day one — I'm building the system so we don't need a full-time PM for routine coordination.
And so that a future Program Manager inherits a running machine instead of chaos.
Without the system
Work lands on Emi
Ad hoc status requests
Handover bar invented at the end
Bottlenecks invisible until too late
→
WITH THE SYSTEM
Emi orchestrates
Status pulled from the record
Handover bar agreed at the start
Heat-map surfaces bottlenecks early

## Slide 16
The proof
Ask it. Don't read it.
AUTODESK
16 / 17

## Slide 17
AUTODESK
17 / 17
THE PROOF
You're not looking at a microsite — you're looking at Phase 6 early
Nobody reads the three-page doc; they skim half and ask again.
So the delivery is a short clip plus an assistant you can just ask. The site you've seen is that, working.
The portfolio learnings library and this assistant are the same thing seen twice: a record you can question.
Ask about the operating system
How do I keep visibility without holding a status meeting?
ASK
The medium proves the message
WHAT I WANT FROM THE TEAM
Where does this model break against how you actually work?
What's the one standard worth making non-negotiable — and what should I drop?
Who owns the PM gap until we solve it? And what's the current state I should confirm before I harden anything?